## Daily Gantt Chart Template
Griptz Tech Ad Gantt Chart
Task ID | Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25
PRE-PRODUCTION
1 | Client Finalization | bar: Week 1 to Week 4
2 | Concept Devleopment | bar: Week 2 to Week 4
3 | Research | bar: Week 2 to Week 9
4 | Scripwriting | bar: Week 4 to Week 9
5 | Storyboarding | bar: Week 6 to Week 9
PPRODUCTION
1 | Environment Modelling | bar: Week 9 to Week 11
2 | Environment Texturing | bar: Week 10 to Week 13
3 | Environment Assembly | bar: Week 12 to Week 13
4 | Assets Design | bar: Week 9 to Week 14
5 | Motion Graphics | bar: Week 11 to Week 15
6 | Animation | bar: Week 13 to Week 16
7 | Camera Animation | bar: Week 16 to Week 17
8 | Lighting | bar: Week 14 to Week 17
9 | Rendering | bar: Week 17 to Week 19
POST-PPRODUCTION
1 | Compositing | bar: Week 19 to Week 20
2 | Editing | bar: Week 20 to Week 21
3 | Visual Effects | bar: Week 21 to Week 22
4 | Color Grading | bar: Week 22 to Week 23
5 | Sound Design | bar: Week 22
6 | Titles and Credits | bar: Week 23
7 | Final Tocuh | bar: Week 23 to Week 24
8 | Review & Feedback | bar: Week 24
DOCUMENTATION
1 | Coursework 1 | bar: Week 1 to Week 10
2 | Coursework 2 | bar: Week 11 to Week 25
3 | Coursework 3 | bar: Week 11 to Week 25

## ©
© TemplateLab.com